## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US_01 | Collect and preprocess KYC documents (OCR, cleaning) | Must Have | Data availability | Bhavyasri | Completed
Sprint 2 | Sprint 2 | US_02 | Develop AI models – CNN (tampering), NLP (text), GNN (duplicate identity) | Must Have | Cleaned data from Sprint 1 | Bhavyasri | Completed
Sprint 3 | Sprint 3 | US_03 | Integrate fraud score with AML rules and real-time pipeline | Should Have | Model outputs from Sprint 2 | Bhavyasri | Completed
Sprint 4 | Sprint 4 | US_04 | Build web UI and admin dashboard for KYC upload, fraud alerts, audit logs | Must Have | Backend APIs | Bhavyasri | Completed
Sprint 4 | Sprint 4 | US_05 | Deployment, end-to-end testing, performance validation | Must Have | All previous sprints | Bhavyasri | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US_02 | T_01 | Build OCR extraction module | 2025-09-01 | 2025-09-03 | Ravi | Development | Completed | 8 | Day 1: Done
US_02 | T_02 | Fine-tune NLP model for address verification | 2025-09-03 | 2025-09-06 | Sneha | Model Training | Completed | 12 | Day 1: Done; Day 2: Done; Day 3: Done
US_02 | T_03 | Train CNN model to detect document tampering | 2025-09-06 | 2025-09-09 | Bhanu | Model Training | Completed | 10 | Day 2: Done; Day 3: Done; Day 4: Done; Day 5: Done
US_02 | T_04 | Train GNN model to detect duplicate Aadhaar identities | 2025-09-09 | 2025-09-12 | Arjun | Research/Implementation | Completed | 14 | Day 3: Done; Day 4: Done; Day 5: Done; Day 6: Done; Day 7: Done; Day 8: Done
US_02 | T_05 | Validate models and compare accuracy | 2025-09-12 | 2025-09-14 | Team | Testing | Completed | 6 | Day 7: Done; Day 8: Done; Day 9: Done; Day 10: Done; Day 11: Done
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 3 | Day 1 | Model inference slow | Optimized GNN & caching
Sprint 3 | Day 2 | AML rule dataset missing | Created synthetic blacklist
Sprint 3 | Day 3 | Admin alerts not showing | Fixed API + notifications
Sprint 3 | Day 4 | JWT auth issues | Added token authentication
Sprint 3 | Day 5 | Everything stable | Final pipeline testing

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
2 | Sprint 4 | 2025-09-20 | 2025-10-04 | Bhavyasri | Implement CI/CD & containerization | Skipping UI documentation | Improving AI model accuracy and pipeline stability | Created Docker setup and improved model integration
3
4
5
6
7