## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Self | 2025-09-03 | OCR not extracting address | Sprint 1 | Self | Functional | Added multi-line config | 2025-09-04 | Closed | OK
2 | Self | 2025-09-07 | GNN giving NaN values | Sprint 2 | Self | Model | Normalized graph data | 2025-09-08 | Closed | Stable
3 | Self | 2025-09-10 | Fraud score API delay | Sprint 3 | Self | Performance | Added async + caching | 2025-09-11 | Closed | 35% faster
4 | Self | 2025-09-15 | Alerts not visible in admin | Sprint 4 | Self | UI/API | Fixed alert trigger | 2025-09-16 | Closed | Verified

## Sheet2
Logical
User Interface
Maintainability
Standards
Others